## Sheet1
Bug ID | Title/Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reporter & Date | Assigned To | Environment | Attachments/References
BUG _1 | After selecting the “Sort by Price: Low to High” option the products are not displayed in ascending order of price on product page | After selecting the “Sort by Price: Low to High” option some products are sorted correctly while others are not that display incorrect sorting order on the product page. | 1-navigate to Featured Categories 2-choose product categorie 3. Select the “Sort by Price: Low to High” option | After sorting products should be displayed in ascending order of price from low price to high price. | After selecting the “Sort by Price: Low to High” option some products are sorted correctly while others are not sorted that make the list is not sorted correctly | Medium | High | New | Mostafa Mohamed– 25-Oct-2025 | Backend Developer | Operatin System"Windows 10" Browser"Microsoft Edge Version 141.0.3537.92 "
BUG _2 | After selecting the “Sort by Price: High to low” option the products are not displayed in descending order of price on product page | After selecting the “Sort by Price: High to low” option some products are sorted correctly while others are not that display incorrect sorting order on the product page. | 1-navigate to Featured Categories 2-choose product categorie 3. Select the “Sort by Price: High to low” option | After sorting products should be displayed in descending order of price from high price to low price. | After selecting the “Sort by Price: High to low” option some products are sorted correctly while others are not sorted that make the list is not sorted correctly | Medium | High | New | Mostafa Mohamed– 25-Oct-2026 | Backend Developer | Operatin System"Windows 10" Browser"Microsoft Edge Version 141.0.3537.92 "
BUG_3 | Customer is able to select both “Has Deal: Yes” and “Has Deal: No” filters in same time on the product page | When applying the “Has Deal” filter on the product page the system allows the user to select both “Yes” and “No” options on same time that display both has deal and non deal products together. | 1-navigate to Featured Categories 2-choose product categorie 3- Open the “Has Deal” dropdown list. 4-Select No from the dropdown list 5- Then select Yes From dropdown list | The system should allow selecting only one option in the "Has Deal" dropdown list "Has deal:Yes" OR "Has deal:No" | After applying the “Has Deal” filter on the product page the system allows the user to select both “Yes” and “No” options on same time that display both has deal and non deal products together | Medium | Medium | New | Mostafa Mohamed– 25-Oct-2027 | Backend Developer | Operatin System"Windows 10" Browser"Microsoft Edge Version 141.0.3537.92 "
BUG _4 | After removing a product from the wishlist on the Home page or Product page a confirmation message is displayed but the product still exists in the wishlist. | After adding a product to the wishlist from the Home Page or Product Page and then removing it a confirmation message appears but the product still appears in the wishlist | 1-Navigate to product exist already on wishlist. 2- Click "Heart" icon. | After removing Product from product page product should disappears from wishlist | After removing Product from wishlist on home page or products page a message appears that the product has been removed but the product still remains in the wishlist. | High | High | New | Mostafa Mohamed– 25-Oct-2028 | Backend Developer | Operatin System"Windows 10" Browser"Microsoft Edge Version 141.0.3537.92 " | BUG_4
BUG_5 | Wishlist icon counter does not appear and does not display the product count | the wishlist icon counter is not appear and it dont display the total number of products added to the wishlist. | 1-Add product to wishlist. | After Adding product to wishlist counter should increase by 1 | After Adding item to wishlist the counter dosent appear and dont incremented by 1 | Medium | High | New | Mostafa Mohamed– 25-Oct-2029 | Frontend Developer | Operatin System"Windows 10" Browser"Microsoft Edge Version 141.0.3537.92 " | BUG_5
BUG _6 | Wishlist icon counter does not appear and does not display the product count | the wishlist icon counter is not appear and it dont display the total number of products removed from the wishlist. | 1-Remove product from wishlist . | After removing product from Wishlist counter should decrease by 1 | After Removing item from whishlist the counter dosent appear and dosent decremented by 1 | Medium | High | New | Mostafa Mohamed– 25-Oct-2030 | Frontend Developer | Operatin System"Windows 10" Browser"Microsoft Edge Version 141.0.3537.92 " | BUG_6
BUG _7 | "Notify Me” button is not clickable on the out-of-stock product details page | “Notify Me” button is not clickable and dont make action on the out-of-stock product details page | 1-Navigate to the Product Details page of an out-of-stock product. 2-click on “Notify Me” button | After clicking the “Notify Me” button it should be clickable | After clicking on "Notify Me" button no action happen | High | High | New | Mostafa Mohamed– 25-Oct-2031 | Frontend Developer | Operatin System"Windows 10" Browser"Microsoft Edge Version 141.0.3537.92 " | BUG_7
BUG_8 | When user is logged in then logs out and selects products, the checkout page is open but is empty | When user is logged in then logs out and selects products from the products page and opens the cart page then presses on the checkout button, the checkout is empty and if the user refreshes the page the checkout shows that the total amount is "Free" and the message "You have 0 products in your cart" is displayed | 1. Log in with a valid user 2. Log out 3. Select products from products page 4. Go to cart page 5. press the checkout button | The checkout page should open showimg that the user needs to log in if they have an existing account or sign up if they don't. If the user refreshes the page, the same content should appear | the checkout page is empty and If the user refreshes the page the checkout page is displays that the total amount is "Free" and this message is displayed "You have 0 products in your cart" | Critical | High | New | Karim Tamer, 27/10/2025 | Development team | Google Chrome Version 138.0.7204.192
BUG_9 | Verify that save the location when you close the page and log in again. | When you enter the location information without logging in and close the page and return to it another time, you will be asked to enter the location again. | Select any city, select any region, select any district Close the page and open it again | Proof of location until the purchase process is completed | Re-enter the place | Medium | Medium | New | Ibrahim A. Hamada . 25-10-2025 | Development team | Google Chrome Version 138.0.7204.192
BUG_10 | Verify that an error message appears that you must log in when you click on Save my place | When entering the location information and clicking on Save My Location, an error message does not appear stating that I must log in to save the location. | Select any city, select any region, select any district Click on Save My Location | Proof of location until the purchase process is completed | null | Medium | Medium | New | Ibrahim A. Hamada . 25-10-2025 | Development team | Google Chrome Version 138.0.7204.192
BUG_11 | Short, clear title for the bug | Detailed explanation of the bug | Step-by-step actions to reproduce the issue | What should happen ideally | What actually happens | Impact level (Critical, Major, Minor, Trivial) | Urgency for fixing (High, Medium, Low) | Current status (New, In Progress, Fixed, Retest, Closed) | Name of the person who found and reported the bug Date when the bug was reported | Developer or team responsible for fixing it | Environment details (OS, browser, app version, etc.) | Links or filenames for screenshots, videos, or logs
BUG_12 | Title: The system does not validate or verify the phone number in the Address Book section and confirms the order with an incorrect number | After logging into the website, navigate to your profile and open the Address Book section. Click on “Add New Address”, and the Add New Address page will open. Fill in all the required fields and enter an invalid phone number ("012345678992"). The system accepts the invalid number without displaying any validation message. Later, when you place an order using this address, the order is confirmed successfully, even though the phone number is incorrect. | Navigate to https://www.seoudisupermarket.com Log in with valid credentials. Go to Profile Then Address Book. Click on Add New Address. Enter a phone number with invalid format (012345678992). Click on Save Address. Go to Checkout and select this address to place an order. Complete the order process. | The system should validate the phone number and display an appropriate error message prompting the user to enter a valid number before saving the address or placing the order. | The system should validate the phone number and display an appropriate error message prompting the user to enter a valid number before saving the address or placing the order No OTP verification was sent to confirm The number | Critical | High | New | Ahmed sherif (29/10/2025) | Developer or team responsible for fixing it | Operatin System "Windows 11" Browser "Firefox Version 144.0(64-bit) " | https://drive.google.com/file/d/1WlXXsQNWB5A2_xVnzCi660jXagAgIKOs/view?usp=drive_link